## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Introduction & Cyber Scan Problem Understanding | MUST HAVE | No Dependency | Dhanush, Noor Nabeeha, Sujithraa, Akshay, Eswar | 3- Completed
S1 | S1 | US-001 | Study of VirusTotal API | MUST HAVE | VirusTotal Docs | Dhanush, Noor Nabeeha, Sujithraa, Akshay, Eswar | 3- Completed
S2 | S2 | US-001 | Study of Nmap (Network Scanning Concepts) | MUST HAVE | Nmap Docs | Dhanush, Noor Nabeeha, Sujithraa, Akshay, Eswar | 3- Completed
S2 | S2 | US-001 | Learning Data Visualization & Dashboarding using Streamlit | MUST HAVE | Streamlit Docs | Dhanush, Noor Nabeeha, Sujithraa, Akshay, Eswar | 3- Completed
S3 | S3 | US-001 | Implementation of Nmap Scan Module | MUST HAVE | Python-nmap | Noor Nabeeha K | 3- Completed
S3 | S4 | US-001 | Implementation of VirusTotal Scan Module | MUST HAVE | Requests Library | Dhanush Polasi | 3- Completed
S4 | S4 | US-001 | Risk Scoring System | MUST HAVE | Custom Logic | Sujithraa, Akshay Bakale | 3- Completed
S4 | S5 | US-001 | Threat Classification & Score Refinement | MUST HAVE | Risk Model | Dhanush Polasi | 3- Completed
S5 | S5 | US-001 | Initial Dashboard Development using Streamlit | MUST HAVE | Streamlit | Noor Nabeeha K | 3- Completed
S5 | S6 | US-001 | Data Visualization | SHOULD HAVE | Matplotlib / Plotly | Noor Nabeeha K | 3- Completed
S6 | S6 | US-001 | Email Alert System for High-Risk Threats | SHOULD HAVE | SMTP / Email API | Noor Nabeeha K | 3- Completed
S6 | S7 | US-001 | Learning Database Concepts & Integration | MUST HAVE | PostgreSQL Docs | Dhanush, Noor Nabeeha, Sujithraa, Akshay, Eswar | 3- Completed
S7 | S7 | US-001 | Database Implementation using PostgreSQL | SHOULD HAVE | PostgreSQL | Eswar | 3- Completed
S7 | S8 | US-001 | Scan Comparison Feature | SHOULD HAVE | SQL Queries | Eswar | 3- Completed
S8 | S8 | US-001 | Dashboard Enhancement | SHOULD HAVE | Streamlit | Noor Nabeeha K | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
[8 empty] | 93 | 21 | 19 | 16 | 16 | 14 | 7 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Project Introduction & Problem Understanding | 2025-01-31 | 2025-02-01 | All | Others | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Study of VirusTotal API | 2025-02-02 | 2025-02-06 | All | Research | 3- Completed | 5 | 0 | 0 | 2 | 1 | 1 | 0 | 0
SPRINT 2 BACKLOG
US-001 | 3 | Study of Nmap | 2025-02-07 | 2025-02-10 | All | Research | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0
US-001 | 4 | Learn Streamlit Dashboarding | 2025-02-11 | 2025-02-13 | All | Research | 3- Completed | 6 | 0 | 0 | 0 | 2 | 2 | 2 | 0
SPRINT 3 BACKLOG
US-001 | 5 | Implement Nmap Scan Module | 2025-02-14 | 2025-02-17 | Noor Nabeeha | Coding | 3- Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0
US-001 | 6 | Implement VirusTotal Scan Module | 2025-02-18 | 2025-02-20 | Dhanush | Coding | 3- Completed | 8 | 0 | 0 | 0 | 2 | 3 | 3 | 0
SPRINT 4 BACKLOG
US-001 | 7 | Risk Scoring System | 2025-02-21 | 2025-02-24 | Sujithraa, Akshay | Coding | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0
US-001 | 8 | Threat Classification & Refinement | 2025-02-25 | 2025-02-27 | Dhanush | Coding | 3- Completed | 5 | 0 | 0 | 0 | 2 | 2 | 1 | 0
SPRINT 5 BACKLOG
US-001 | 9 | Initial Dashboard using Streamlit | 2025-02-28 | 2025-03-03 | Noor Nabeeha | Build | 3- Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0
US-001 | 10 | Data Visualization (Charts) | 2025-03-04 | 2025-03-06 | Noor Nabeeha | Build | 3- Completed | 6 | 0 | 0 | 0 | 3 | 2 | 1 | 0
SPRINT 6 BACKLOG
US-001 | 11 | Email Alert System | 2025-03-07 | 2025-03-09 | Noor Nabeeha | Integration | 3- Completed | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0
US-001 | 12 | Learn PostgreSQL & DB Concepts | 2025-03-10 | 2025-03-13 | All | Research | 3- Completed | 4 | 0 | 0 | 2 | 1 | 1 | 0 | 0
SPRINT 7 BACKLOG
US-001 | 13 | Store Scan Results in Database | 2025-03-14 | 2025-03-17 | Eswar | Coding | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0
US-001 | 14 | Scan Comparison Feature | 2025-03-18 | 2025-03-20 | Eswar | Coding | 3- Completed | 6 | 0 | 0 | 3 | 1 | 2 | 0 | 0
SPRINT 8 BACKLOG
US-001 | 15 | Dashboard Enhancement (Filters, UI Improvements) | 2025-03-21 | 2025-03-24 | Noor Nabeeha | System Build | 3- Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0
US-001 | 16 | Final Testing & Integration | 2025-03-25 | 2025-03-27 | All | System Test | 3- Completed | 6 | 0 | 0 | 2 | 3 | 1 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 4 | Difficulty parsing complex JSON responses during the VirusTotal API research. | Conducted a team review of the API documentation and tested sample queries to standardize data extraction.
Sprint 2 | Day 10 | Confusion regarding Streamlit's state management and layout constraints for the dashboard. | Researched Streamlit's session state and container structures to mock up a reliable UI framework.
Sprint 3 | Day 18 | VirusTotal and Nmap scan modules were blocking execution due to synchronous API calls. | Refactored the module logic to handle requests more efficiently and prevent the application from hanging.
Sprint 4 | Day 25 | Challenges standardizing the risk scoring system across entirely different types of threat classifications. | Developed a unified risk matrix to map diverse Nmap and VirusTotal vulnerabilities to a standard severity scale.
Sprint 5 | Day 32 | Data visualization charts were not updating dynamically when fresh scan data was introduced. | Collaborated to debug the underlying dataframe structures and properly implement st.rerun().
Sprint 6 | Day 38 | SMTP authentication failures when attempting to configure the new Email Alert System. | Generated app-specific passwords and isolated credentials into secure environment variables.
Sprint 7 | Day 46 | Difficulty designing a PostgreSQL schema flexible enough to store nested, variable scan results. | Held a database design session to normalize the tables for hosts, scans, and vulnerabilities.
Sprint 8 | Day 53 | Integration conflicts arose when merging the scan comparison feature with the final dashboard filters. | Conducted a full-team system testing session to squash bugs and ensure seamless UI interactions.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-01-31 | 2025-02-06 | All | Reviewing API limits and JSON response structures before writing logic. | Underestimating the time needed to thoroughly research new APIs. | Collaborative brainstorming to align on project workflow. | Standardized data extraction methods for API responses.
2 | Sprint 2 | 2025-02-07 | 2025-02-13 | Noor Nabeeha | Prototyping basic UI layouts early to understand Streamlit's constraints. | Getting bogged down by advanced Nmap flags before nailing the basics. | Sharing helpful tutorials and documentation with the team. | Created a basic Streamlit skeleton app to test state management.
3 | Sprint 3 | 2025-02-14 | 2025-02-20 | Dhanush | Using environment variables for secure credential management. | Hardcoding API keys directly into the scan module scripts. | Dividing complex modules like Nmap and VirusTotal to work in parallel. | Refactored module logic to handle requests efficiently.
4 | Sprint 4 | 2025-02-21 | 2025-02-27 | Sujithraa, Akshay | Defining unified data structures before coding the logic. | Working in silos on features that heavily overlap like scoring and classification. | Regular quick sync-ups to ensure the threat logic aligns. | Integrated a unified risk matrix to map diverse vulnerabilities.
5 | Sprint 5 | 2025-02-28 | 2025-03-06 | Noor Nabeeha | Implementing dynamic data handling using Streamlit session states early on. | Relying too heavily on static mock data for dashboard visualizations. | Focusing on clean, user-friendly, and scannable charts. | Debugged underlying dataframe structures to ensure charts update dynamically.
6 | Sprint 6 | 2025-03-07 | 2025-03-13 | All | Designing database schemas collaboratively before writing insertion code. | Overlooking SMTP edge cases . | Thoroughly testing third-party integrations. | Secured SMTP configs with app passwords and normalized DB tables.
7 | Sprint 7 | 2025-03-14 | 2025-03-20 | Eswar | Running quick regression tests before pushing final DB storage commits. | Pushing backend changes without double-checking the frontend UI impact. | Displaying strong teamwork and communication during bug fixing. | Conducted a system test to ensure DB results load properly into the dashboard.